## Consulting Stages
Stage Number | Short Label | Title | Purpose | Gate | Gate Criteria | Frameworks | Actions | Deliverables | Questions Answered | Journey Label
0 | Qualify | Account and Opportunity Qualification | Determine whether there is a genuine client problem, executive interest, budget and sufficient opportunity for an AI engagement. | Pursuit Gate | A credible business need exists ¦ An executive or senior stakeholder is engaged ¦ The opportunity is aligned with consulting capabilities ¦ There is a reasonable path to funding | BANT ¦ MEDDICC ¦ Stakeholder Power–Interest Grid ¦ Client Context Canvas ¦ PESTLE ¦ Porter's Five Forces ¦ Business Model Canvas ¦ Strategic Value Hypothesis ¦ MECE issue decomposition | Create client record ¦ Add opportunity name and description ¦ Identify client industry and geography ¦ Record business drivers ¦ Identify initial stakeholders ¦ Record known challenges ¦ Capture estimated opportunity size ¦ Assess engagement fit ¦ Record conflicts, procurement constraints and dependencies ¦ Set pursuit decision | Client opportunity brief ¦ Stakeholder map ¦ Initial value hypothesis ¦ Qualification score ¦ Go/no-go recommendation ¦ Initial meeting plan | Why is the client considering AI? ¦ What business outcomes are they seeking? ¦ Is the opportunity strategically relevant? ¦ Is there an executive sponsor? ¦ Is there likely to be sufficient value? ¦ Should the consulting team pursue the opportunity? | Qualify
1 | Introduce | First Client Meeting and Executive Introduction | Build trust, understand the client context and agree the next step without prematurely proposing technology. | Discovery Authorisation Gate | The client agrees to continue into a structured discovery or assessment | SPIN questioning ¦ Five Whys ¦ Active listening ¦ Jobs to Be Done ¦ Pyramid Principle ¦ Situation–Complication–Question–Answer ¦ Stakeholder mapping ¦ Hypothesis-driven consulting | Generate first-meeting agenda ¦ Record meeting notes ¦ Tag business problems ¦ Record stakeholder interests ¦ Create assumptions ¦ Capture decisions ¦ Generate follow-up actions ¦ Generate a meeting summary ¦ Create an opportunity hypothesis tree | First meeting summary ¦ Client problem statement ¦ Initial engagement hypothesis ¦ Stakeholder register ¦ Proposed discovery approach ¦ Follow-up email ¦ Evidence request list | What are the top three business priorities? ¦ Where is the organisation under the most pressure? ¦ What outcomes would make this engagement successful? ¦ What AI initiatives already exist? ¦ Who would sponsor the programme? | Introduce
2 | Mobilise | Proposal, Scope and Mobilisation | Convert the client need into a controlled engagement with clear outcomes, scope, governance and responsibilities. | Mobilisation Gate | Scope, commercial terms, stakeholders and acceptance criteria are agreed | Project Charter ¦ Statement of Work ¦ RACI ¦ RAID ¦ Work Breakdown Structure ¦ MoSCoW ¦ Deliverables-based planning ¦ Success Measures and OKRs | Define engagement objectives ¦ Define in-scope and out-of-scope areas ¦ Select consulting workstreams ¦ Define deliverables ¦ Build delivery timeline ¦ Allocate consulting and client resources ¦ Create RACI ¦ Define governance meetings ¦ Create quality review gates ¦ Define assumptions and dependencies ¦ Define acceptance criteria ¦ Generate the proposal and Statement of Work | Proposal ¦ Statement of Work ¦ Project Charter ¦ Detailed delivery plan ¦ RACI ¦ RAID log ¦ Communications plan ¦ Evidence request tracker ¦ Deliverables register ¦ Quality assurance plan | What are the engagement objectives? ¦ What is in and out of scope? ¦ Who is accountable for each workstream? ¦ What are the acceptance criteria? | Mobilise
3 | Discover | Current-State Discovery | Understand the client's strategy, organisation, processes, technology, data, skills, governance and existing AI capabilities. | Current-State Validation Gate | Business, technology and risk stakeholders confirm the assessment represents the organisation | SWOT ¦ PESTLE ¦ Porter's Five Forces ¦ Business Model Canvas ¦ Value Chain Analysis ¦ Capability Mapping ¦ MECE ¦ SIPOC ¦ BPMN ¦ Value Stream Mapping ¦ Customer Journey Mapping ¦ McKinsey 7S ¦ TOGAF ¦ C4 ¦ DAMA principles | Schedule stakeholder interviews ¦ Create customised interview questionnaires ¦ Upload and classify client evidence ¦ Map business capabilities ¦ Create process maps ¦ Build application and data-source inventories ¦ Record existing AI systems ¦ Score organisational capabilities ¦ Record problems and root causes ¦ Link evidence to findings ¦ Identify evidence gaps ¦ Generate current-state diagrams ¦ Create an initial findings register | Current-State Assessment ¦ Business Capability Map ¦ Process Maps ¦ Technology Architecture ¦ Application Inventory ¦ Data Inventory ¦ AI System Inventory ¦ Skills Assessment ¦ Governance Assessment ¦ Current-State Findings Register | What does the current operating model look like? ¦ Which processes, systems and data sources matter? ¦ Where are the evidence gaps? | Discover
4 | Assess | AI Maturity and Readiness Assessment | Determine whether the organisation has the capabilities needed to introduce and scale AI. | Readiness Agreement Gate | Management agrees on current maturity, target maturity and priority capability gaps | AI Maturity Model ¦ NIST AI Risk Management Framework ¦ ISO/IEC 42001 ¦ Data Maturity Model ¦ Cloud Adoption Framework ¦ Capability Maturity Model ¦ Skills Heatmap | Issue maturity questionnaires ¦ Collect supporting evidence ¦ Score each maturity dimension ¦ Compare stakeholder responses ¦ Identify conflicting perceptions ¦ Define target maturity ¦ Calculate maturity gaps ¦ Generate a heatmap ¦ Recommend capability-building actions ¦ Link gaps to roadmap initiatives | AI Maturity Assessment ¦ Current-versus-target heatmap ¦ Capability gap register ¦ Evidence register ¦ Improvement recommendations ¦ Executive maturity summary | What is the current maturity across strategy, data, tech, governance and talent? ¦ What is the target maturity? ¦ Where are the priority capability gaps? | Assess
5 | Identify | Opportunity Identification and Problem Definition | Identify where AI, analytics, automation or process redesign could generate meaningful business value. | Opportunity Validation Gate | Only well-defined opportunities with owners, baseline evidence and measurable outcomes proceed | Design Thinking ¦ Jobs to Be Done ¦ AI Canvas ¦ Lean AI Canvas ¦ Value Stream Mapping ¦ Five Whys ¦ Fishbone Diagram ¦ How Might We ¦ Problem Statement Canvas ¦ Benefits Dependency Network ¦ MECE opportunity decomposition | Define the business outcome ¦ Map the current process ¦ Identify pain points ¦ Quantify current performance ¦ Identify root causes ¦ Identify affected users and decisions ¦ Identify available data ¦ Generate potential interventions ¦ Test AI suitability ¦ Define expected benefits ¦ Assign a business owner | Opportunity longlist ¦ Use-case cards ¦ Process pain-point maps ¦ Benefits hypotheses ¦ Baseline metrics ¦ Root-cause analysis ¦ AI suitability assessment | What is the simplest intervention capable of solving the problem? ¦ Is this an AI problem or something else? ¦ Who owns the opportunity and baseline metrics? | Identify
6 | Prioritise | Use-Case Prioritisation and Portfolio Design | Select a balanced portfolio of use cases based on value, feasibility, risk and strategic relevance. | Portfolio Approval Gate | Management selects use cases for investment, detailed design or controlled experimentation | Value-versus-Feasibility Matrix ¦ RICE ¦ WSJF ¦ MoSCoW ¦ Risk-adjusted prioritisation ¦ Three Horizons ¦ Portfolio Matrix ¦ Dependency Mapping | Allow custom weights ¦ Score every use case with evidence ¦ Show disagreements between stakeholders ¦ Run alternative scenarios ¦ Display a value-feasibility matrix ¦ Identify portfolio dependencies and foundational enablers ¦ Classify use cases into portfolio categories | Prioritised AI portfolio ¦ Use-case scoring model ¦ Portfolio heatmap ¦ Dependency map ¦ Quick-win shortlist ¦ Strategic investment shortlist ¦ Rejected and deferred use-case register | Which use cases create the best value-feasibility balance? ¦ What are quick wins versus strategic investments? ¦ Which use cases should be deferred or rejected? | Prioritise
7 | Strategise | AI Strategy and Target Operating Model | Define how AI will support the organisation’s strategy and how it will govern, build, buy, deploy and operate AI. | Strategy Approval Gate | Executives agree on ambition, strategic choices, ownership and target operating model | Strategy Choice Cascade ¦ Three Horizons ¦ Target Operating Model ¦ Operating Model Canvas ¦ McKinsey 7S ¦ Build–Buy–Partner ¦ Centralised, federated and hub-and-spoke models ¦ Capability Mapping ¦ North Star and OKRs | Run strategy workshops ¦ Define strategic choices ¦ Compare operating-model options ¦ Map required capabilities ¦ Define decision rights ¦ Identify build, buy and partner decisions ¦ Define target-state organisation ¦ Create a strategy-on-a-page ¦ Generate executive strategy document | AI Strategy ¦ AI Vision and Principles ¦ Target Operating Model ¦ Capability Model ¦ Governance Model ¦ Sourcing Strategy ¦ Talent Strategy ¦ Technology Principles ¦ Strategy-on-a-Page | What is the AI vision and ambition? ¦ What operating model is required? ¦ Build, buy or partner? | Strategise
8 | Govern | Data, Ethics, Governance and Risk Assessment | Ensure selected use cases can be delivered with acceptable data, legal, security, ethical and operational risk. | Responsible AI and Risk Gate | No use case progresses without defined ownership, controls and accepted residual risk | NIST AI RMF ¦ ISO/IEC 42001 ¦ Data Protection Impact Assessment ¦ AI Impact Assessment ¦ Ethics Canvas ¦ Consequence Scanning ¦ STRIDE ¦ OWASP guidance for generative AI ¦ MITRE ATLAS ¦ Bow-Tie Analysis ¦ FMEA ¦ Three Lines Model | Classify AI risk ¦ Conduct privacy screening ¦ Determine whether a DPIA is required ¦ Create threat model ¦ Create human-oversight design ¦ Record controls ¦ Calculate inherent and residual risk ¦ Assign risk owners ¦ Document risk acceptance ¦ Generate governance approval pack | Data Readiness Assessment ¦ AI Impact Assessment ¦ DPIA where required ¦ Security Threat Model ¦ Ethical Risk Assessment ¦ Human-Oversight Plan ¦ AI Risk Register ¦ Control Matrix ¦ Governance Approval Record | Is the data ready and lawful to use? ¦ What ethical and security risks exist? ¦ What residual risk is acceptable? | Govern
9 | Roadmap | Business Case and Roadmap | Convert the AI strategy into a sequenced, funded and measurable transformation plan. | Investment Gate | The client approves funding, resources and initiatives progressing into design and implementation | Total Cost of Ownership ¦ ROI ¦ NPV ¦ Payback period ¦ Cost-benefit analysis ¦ Benefits Dependency Network ¦ FinOps ¦ Three Horizons ¦ Now–Next–Later ¦ Critical Path ¦ Scenario Planning ¦ Sensitivity Analysis | Calculate implementation and operating costs ¦ Model benefit scenarios ¦ Compute ROI, payback and NPV ¦ Sequence roadmap workstreams ¦ Map dependencies and resources ¦ Produce executive funding recommendation | AI Transformation Roadmap ¦ Initiative business cases ¦ TCO model ¦ ROI model ¦ Benefits register ¦ Resource plan ¦ Dependency map ¦ Investment options ¦ Executive funding recommendation | What is the TCO, ROI and payback? ¦ In what sequence should initiatives run? ¦ What funding recommendation should go to executives? | Roadmap
10 | Design | Solution Design | Translate approved use cases into complete business, data, technical, security and operating designs. | Design Authority Gate | Architecture, security, data and product stakeholders approve the solution design | TOGAF ¦ C4 Model ¦ Architecture Decision Records ¦ Domain-Driven Design ¦ Zero Trust ¦ Privacy by Design ¦ Secure by Design ¦ Well-Architected Frameworks ¦ STRIDE ¦ User Story Mapping ¦ Non-functional requirements | Design business process and UX ¦ Define functional and non-functional requirements ¦ Design data, application, integration and model architecture ¦ Design security, observability and human oversight ¦ Compare models and hosting options ¦ Record architecture decisions | Detailed Use-Case Specification ¦ High-Level Design ¦ Low-Level Design ¦ Architecture diagrams ¦ Data-flow diagrams ¦ Integration specification ¦ Security design ¦ Model selection decision ¦ Non-functional requirements ¦ Architecture Decision Records | What is the target architecture? ¦ Which model and platform fit the constraints? ¦ What non-functional requirements apply? | Design
11 | Prototype | Prototype and Proof of Value | Test the most uncertain assumptions before committing to full production delivery. | Proof-of-Value Gate | The use case demonstrates sufficient business value, feasibility and controllable risk | Lean Startup ¦ Build–Measure–Learn ¦ CRISP-DM ¦ Agile experimentation ¦ Hypothesis testing ¦ Design of Experiments ¦ Evaluation scorecards ¦ Red teaming | Define prototype scope and hypothesis ¦ Create experiment backlog ¦ Upload evaluation dataset ¦ Define evaluation rubric ¦ Record test results ¦ Compare models and architecture options ¦ Track defects and limitations ¦ Record user feedback ¦ Generate proceed, revise or stop recommendation | Prototype ¦ Prototype Report ¦ Evaluation Scorecard ¦ User Testing Report ¦ Security Test Results ¦ Cost and Performance Results ¦ Productionisation Gap Assessment ¦ Scale Recommendation | Does the prototype improve the business outcome? ¦ Are quality, cost, latency and risk acceptable? ¦ Proceed, revise or stop? | Prototype
12 | Build | Delivery Planning and Production Build | Convert the validated prototype into a secure, reliable and supportable production service. | Production Readiness Gate | Security, performance, support, data, governance and business acceptance criteria are met | Agile or Scrum ¦ Kanban ¦ DevSecOps ¦ MLOps ¦ LLMOps ¦ CI/CD ¦ Test Pyramid ¦ Definition of Ready ¦ Definition of Done ¦ Release management ¦ Secure Software Development Lifecycle | Finalise requirements and backlog ¦ Build production integrations and data pipelines ¦ Implement identity, guardrails and monitoring ¦ Configure cost limits and recovery ¦ Perform security and performance testing ¦ Complete operational documentation ¦ Conduct user acceptance testing ¦ Prepare deployment and rollback plans | Production solution ¦ Product backlog ¦ Test plan and evidence ¦ Security assessment ¦ Release and deployment plans ¦ Rollback plan ¦ Operational runbook ¦ Model or system card ¦ User acceptance sign-off | What must be true for production readiness? ¦ Are security, performance and UAT gates passed? | Build
13 | Adopt | Change Management and Adoption | Ensure that employees understand, trust and use the solution appropriately. | Adoption Readiness Gate | Users, support teams and managers demonstrate sufficient readiness for go-live | ADKAR ¦ Kotter Eight-Step Model ¦ Stakeholder Impact Assessment ¦ Change Impact Matrix ¦ Learning Needs Analysis ¦ Training Evaluation ¦ Change Network Model | Identify impacted roles ¦ Assess process and responsibility changes ¦ Create stakeholder personas ¦ Build communication and training plans ¦ Establish champion network ¦ Track training attendance and adoption ¦ Collect feedback and record resistance ¦ Define reinforcement actions | Change Strategy ¦ Change Impact Assessment ¦ Stakeholder Engagement Plan ¦ Communication Plan ¦ Training Plan ¦ AI Champions Structure ¦ User Guides ¦ Adoption Dashboard ¦ Resistance and Feedback Register | Who is impacted and what must they learn? ¦ Is adoption readiness sufficient for go-live? | Adopt
14 | CoE | AI Centre of Excellence and Operating Model Implementation | Create permanent organisational capability for scaling and governing AI. | Operating Model Activation Gate | Ownership is established for strategy, governance, delivery and operational support | Centralised, federated, decentralised and hub-and-spoke models ¦ Target Operating Model ¦ RACI ¦ Service Catalogue | Define CoE charter and responsibilities ¦ Stand up policy and pattern libraries ¦ Create approved model and vendor registers ¦ Establish use-case inventory and risk register ¦ Build evaluation library and training materials ¦ Capture lessons learned and innovation backlog | AI CoE Charter ¦ CoE Operating Model ¦ CoE RACI ¦ Service Catalogue ¦ Governance Calendar ¦ Capability Development Plan ¦ Reusable Pattern Library ¦ Community of Practice Plan | Which operating model fits the organisation? ¦ What services will the CoE provide? | CoE
15 | Deploy | Go-Live and Service Transition | Move the solution from project delivery into a stable, supported production service. | Go-Live Gate | Business, technology, security, governance and support owners jointly approve production launch | ITIL ¦ Service Transition ¦ Operational Readiness Review ¦ RACI ¦ Service Acceptance Criteria ¦ SRE principles ¦ Release and deployment management | Confirm business, product, service, technical, data, risk and support owners ¦ Complete runbooks, model cards and escalation processes ¦ Verify monitoring, alerting, access, backup and recovery ¦ Activate support queue and incident process ¦ Obtain joint go-live approval | Service Transition Plan ¦ Operational Readiness Assessment ¦ Support Model ¦ Service Catalogue Entry ¦ Runbook ¦ Knowledge Base ¦ Incident and Escalation Process ¦ Business Continuity Plan ¦ Go-Live Approval | Are ownership, documentation and operations ready? ¦ Do all owners approve go-live? | Deploy
16 | Support | SLA, Service and Support Management | Provide clear performance, support, availability and accountability commitments after deployment. | Service Commitment Gate | Service indicators, targets and support ownership are agreed and measurable | ITIL Service Level Management ¦ SRE ¦ Service Level Indicators ¦ Service Level Objectives ¦ Service Level Agreements ¦ Error budgets ¦ Incident, problem and change management | Create SLA and define service indicators and targets ¦ Connect monitoring data ¦ Record breaches and manage service credits ¦ Track incidents and root-cause analysis ¦ Review recurring issues ¦ Generate monthly service report | SLA ¦ Operational Level Agreements ¦ Support Handbook ¦ Service Dashboard ¦ Incident Reports ¦ Problem Records ¦ Monthly Service Report ¦ SLA Breach Register | What SLIs, SLOs and SLAs apply? ¦ How are incidents and breaches managed? | Support
17 | Optimise | AI Operations, Monitoring and Continuous Improvement | Monitor whether the system remains safe, accurate, cost-effective and valuable. | Operations Health Gate | Technical, AI quality, business, risk and cost signals are actively monitored | MLOps ¦ LLMOps ¦ SRE ¦ FinOps ¦ NIST AI RMF Measure and Manage ¦ PDCA ¦ Model monitoring ¦ Benefits realisation | Integrate monitoring dashboards ¦ Track model and prompt versions ¦ Track evaluation history ¦ Record incidents and reassess risk ¦ Monitor costs versus expected value ¦ Create improvement backlog ¦ Trigger retraining or prompt changes ¦ Schedule governance reviews | AI Operations Dashboard ¦ Model Performance Report ¦ Cost Report ¦ Risk Monitoring Report ¦ Benefits Realisation Report ¦ Improvement Backlog ¦ Model Change Record ¦ Periodic Governance Review | Is quality, cost and risk within tolerance? ¦ What improvements should enter the backlog? | Optimise
18 | Expand | Executive Value Review and Expansion | Determine whether the initiative delivered expected value and whether it should be scaled, changed or stopped. | Expansion Decision Gate | Executives decide to scale, continue, improve, re-platform, restrict, pause or retire | Benefits Realisation Management ¦ OKRs ¦ Balanced Scorecard ¦ Portfolio Review ¦ Three Horizons ¦ Lessons Learned ¦ After Action Review | Compare actual performance with baseline and business case ¦ Identify adoption barriers and cost variances ¦ Review incidents and risks ¦ Identify reusable assets ¦ Determine whether to expand ¦ Update portfolio and maturity assessment ¦ Recommend next investment cycle | Executive Value Review ¦ Benefits Realisation Report ¦ Lessons Learned ¦ Scaling Recommendation ¦ Updated AI Roadmap ¦ Updated Portfolio ¦ Renewal or Expansion Proposal | Did we achieve the business case? ¦ Scale, improve, restrict, pause or retire? | Expand
19 | Close | Engagement Closure and Handover | Complete consulting responsibilities, transfer ownership and ensure outstanding actions are controlled. | Closure Gate | Deliverables are accepted, operational ownership is confirmed and outstanding risks have named owners | Engagement Closure Checklist ¦ Knowledge Transfer ¦ Lessons Learned | Collate all deliverables and confirm approval status ¦ Identify open risks and hand over action log ¦ Transfer repositories and credentials through approved channels ¦ Complete knowledge transfer ¦ Confirm support ownership ¦ Close commercial items ¦ Capture client feedback ¦ Archive engagement ¦ Convert reusable assets into templates | Final Engagement Report ¦ Handover Pack ¦ Deliverables Index ¦ Open Actions Register ¦ Open Risks Register ¦ Knowledge Transfer Record ¦ Closure Report ¦ Client Acceptance ¦ Lessons Learned | Are deliverables accepted? ¦ Is operational ownership confirmed? ¦ Do open risks have named owners? | Close

## Business Situations
Situation ID | Label | Recommended Stages | Recommended Frameworks
understand-business | Understand the client’s business | stage-0 ¦ stage-1 ¦ stage-3 | Business Model Canvas ¦ PESTLE ¦ Porter's Five Forces ¦ MECE
identify-problems | Identify business problems | stage-1 ¦ stage-3 ¦ stage-5 | SPIN questioning ¦ Five Whys ¦ Issue trees ¦ MECE
underperforming-process | Analyse an underperforming process | stage-3 ¦ stage-5 | SIPOC ¦ BPMN ¦ Value Stream Mapping ¦ Five Whys ¦ Fishbone Diagram ¦ MECE
ai-opportunities | Identify AI opportunities | stage-5 | AI Canvas ¦ Jobs to Be Done ¦ How Might We ¦ Lean AI Canvas
ai-maturity | Assess AI maturity | stage-4 | AI Maturity Model ¦ NIST AI RMF ¦ ISO/IEC 42001 ¦ Skills Heatmap
prioritise-use-cases | Prioritise use cases | stage-6 | Value-versus-Feasibility Matrix ¦ RICE ¦ WSJF ¦ Dependency Mapping
ai-strategy | Develop an AI strategy | stage-7 | Strategy Choice Cascade ¦ Target Operating Model ¦ Three Horizons ¦ Build–Buy–Partner
data-readiness | Assess data readiness | stage-3 ¦ stage-8 | Data maturity model ¦ Data quality dimensions ¦ DAMA principles
evaluate-risk | Evaluate risk | stage-8 | NIST AI RMF ¦ ISO/IEC 42001 ¦ STRIDE ¦ AI Impact Assessment
business-case | Build a business case | stage-9 | TCO ¦ ROI ¦ NPV ¦ Benefits Dependency Network
design-solution | Design an AI solution | stage-10 | C4 Model ¦ TOGAF ¦ ADR ¦ Well-Architected Frameworks
run-prototype | Run a prototype | stage-11 | Lean Startup ¦ Build–Measure–Learn ¦ Evaluation scorecards
prepare-production | Prepare for production | stage-12 ¦ stage-15 | DevSecOps ¦ MLOps ¦ LLMOps ¦ Definition of Done
organisational-change | Manage organisational change | stage-13 | ADKAR ¦ Kotter Eight-Step Model ¦ Change Impact Matrix
setup-coe | Set up an AI Centre of Excellence | stage-14 | Target Operating Model ¦ RACI ¦ Service Catalogue
define-service-levels | Define service levels | stage-16 | ITIL Service Level Management ¦ SRE ¦ SLI / SLO / SLA
monitor-value | Monitor value after go-live | stage-17 ¦ stage-18 | Benefits Realisation Management ¦ FinOps ¦ LLMOps ¦ OKRs